## Sheet1
Project Management System
Day | Task | Domain | Description | Status | Testing
1 | Set up Spring Project | Backend | Initialized project using Spring Boot. | Completed | NA
| Backend | Backend | Created database in MySQL and connected it. | Completed | NA
| Manage CSRF & CORS | Backend | CSRF and CORS. | Completed | NA
2 | User signup & signin | Backend | Tested API endpoint wot check with valid/invalid credentials | Completed | Success
| JWT, User Authentication | Backend | Issued JWT token and authorities to users. | Completed | Verified
| User Request | Backend | Request to user to join community | Completed | NA
3 | Chat | Backend | Chat and Command about Project | Completed | Na
| Repository and Service | Backend | JPA Repository for CRUD operations | Pending | Na
| Repository and Service | Backend | JPA Repository for CRUD operations | Pending | Na